Chapter VI

Project Quality Assurance Procedures

1.    Guiding principles for the review and inspection of the project

The following table lists some of the basic principles that must be heeded in order to ensure the quality of the project, including review and inspection mechanisms at each stage to ensure the meeting of Performance Objectives.

Table 26 Basic Principles that Should Guide the Review and Inspection of the Project

- A high performance objective calls for a high degree of specialization among project participants. Special attention must be paid to the analysis and detailing of the components, as well as to building practices and the meticulous inspection of the construction process. - Design and construction should meet the principles and quality criteria of the ISO9000 standard. - At each stage of the project, participating specialists must review the work underway to make sure it meets the standards of their particular discipline. In addition, they should engage in interdisciplinary reviews across disciplines as a form of double-checking. - At each stage of the project (including both design and construction), independent inspections must be carried out. The specialists in charge of the design and construction of the facility must carry out their activities in full awareness that such inspections will take place. - Before the final plans are issued for each of the components or disciplines, a draft must be issued to the various teams of specialists for review and commentary. - All quality standards that the project requires must be documented. No tacit or oral agreements will be accepted. - The Technical Inspection Team must comprise a multidisciplinary group of specialists with expertise proportional to the overall protection requirements of the project. The team must include at least one representative from each of the disciplines listed in table 24. - The Technical Inspection Team must guarantee that all the provisions stipulated in the tender documents are met. - The Technical Inspection Team must make every effort to ensure that its role is preventive rather than corrective. - Each standard system, equipment, or component must be certified to meet the performance objectives of the project. - Any modification to the original project during the construction stage must be approved by all the parties: the Client Institution, the Project Director, the Coordination Team, the specialists, the Technical Inspection Team, and the Contractor. The characteristics of the modification must be described in detail in the As-built Report. - Materials, systems or equipment defined in the project specifications may be replaced by a technical equivalent proposed by the Contractor, subject to the prior approval of all the parties. The characteristics of the technical equivalent must be clearly described in the As-built Report. - Any project involving operational or investment protection objectives calls for an As-built Report. In projects where the performance objective only calls for the safety of the occupants, an As-Built Report must be produced if expressly demanded by the institution or the Coordination Team. - Other principles should be applied if the work group considers them necessary or relevant.

- Project Quality Assurance during the Preliminary and Design Stages

The following table specifies the tasks required for the correct execution of the project in its preliminary stage, including regional and local hazard studies, as well as its design phase.

#### Table 27 #### Quality Assurance Program for the Initial and Design Stages of the Project

#### Project Definition

#### Definition of the objectives and scope of the project

#### Definition of the Participants (see Chapter V)1

#### The Client Institution

#### The Project Director

#### The Planning and Coordination Team

#### The specialists that will integrate the Project Execution Team

#### Participating consultancy firms and other participating firms

#### The Review Team, with representatives from each of the relevant disciplines

#### Assignment of functions and responsibilities, and limits thereof1

#### The Client Institution’s functions and responsibilities

#### The Project Director’s functions and responsibilities

#### The Coordination and Planning Team’s functions and responsibilities

#### The Project Execution Team’s functions and responsibilities

#### Participating consultancy firms and other participating firms’ functions and responsibilities

#### The functions and responsibilities of the Review Team

#### Work Plan

#### Procedures for assessing the professional candidates to the Execution Team

#### Completion schedules for the preliminary risk assessments and other studies, and for designing the facility

#### Overall budget for the assessments, design, and construction of the facility

#### Definition of communication channels and protocols

#### Between the specialists and the Institution, Project Director, and Coordination Team

#### Among and within the various specialist teams

#### Schedule of coordination meetings with representatives of the various specialist teams, the Institution, the Project Director, and the Coordination Team

#### Deadlines for the delivery and update of plans and specifications2

#### Definition of review, follow-up, and control mechanisms

#### Reviews by the Project Director or his or her staff

#### Reviews by the teams of specialists3

#### Reviews across disciplines4

#### External professional inspection

#### Definition of review mechanisms for the final project 5

#### General review regarding the fulfillment of design criteria

#### Review of calculation logs

#### Review of siting plans

#### Review of architectural plans

#### Plans of the various sections of the facility

#### Floor plans

#### Section and elevation plans

#### Architectural detailing and finishing plans

#### Other architectural components (doors, windows, stairs, appendages, signs, etc.)

#### Review of structural plans

#### General specification plans

#### Foundation plans

#### Floor plans

#### Section and elevation plans

#### Structural detailing

#### Review of layout plans for basic facilities, lifelines, clinical gases, A/C ducts, electrical wiring, etc.

#### Review of installation plans for equipment, furnishings and other components

#### Review of plans for details, connections and anchoring of components

#### Review of other plans

#### Review of tender documents

#### Review of technical specifications

#### Review of equipment installation specifications

#### Review of construction and procedures manual

#### Review of general contract conditions

#### Review of units of measures, quantities of materials and so on, completion schedule, construction budget and forms of payment

#### Review of other tender documents

#### Definition of inspection procedures during the construction process

#### Listing of construction procedures that require inspection or specialized inspection, and type of inspection required

#### Listing of components and services that require inspection or specialized inspection, and type of inspection required

#### Characteristics of the expected reports (See Table 29)

| Notes: | 1 | The selection of the participating design professionals, as well as the assignment of responsibilities, must be carried out with special care. Conflicts of interest tend to affect the quality of the project. |
| --- | --- | --- |
|  | 2 | Each discipline must work based on the most up-to-date information issued by the other disciplines in timely fashion. |
|  | 3 | Each plan, technical specification, or tender document must be checked by at least one expert from another discipline than that of the expert who produced it. |
|  | 4 | Multidisciplinary projects need to be checked at each stage by all the disciplines involved. |
|  | 5 | Before the final plans are issued, they must be submitted to the other disciplines for review and commentary. |

#### Project Quality Assurance: the Construction Stage of the Project

The following table specifies the minimum tasks that must be carried out in order to ensure the correct execution of the project in its construction stage.

#### Table 28 Quality Assurance Program for the Construction Stage of the Project

#### Conditions for the start of the construction

#### Final design plans approved

#### Technical specifications approved

#### Tender documents approved by the parties

#### Contract signed

#### Responsibilities of the Client Institution, Project Director and Coordination Team

#### Present the Contractor with a feasible project

#### Provide the necessary financing

#### Provide an adequate site

#### Choose the most suitable Technical Inspection Team

#### Participate in the decision-making process in matters critical to the project or unregulated issues

#### Report to the Specialists and to the Construction Firm, in timely fashion, any modifications to the project

#### Remain up to date on the progress and state of the construction

#### Meet any other responsibilities stipulated in the contract

#### Definition of the Equipment Designer’s functions during the construction stage

#### Report to the Institution, Project Director, and Coordination Team, in timely fashion, any changes to the original project

#### Assist the Technical Inspection Team in protection matters (a interpreter of the technical specifications)

#### Participate in the decision-making process concerning matters critical to the project, or unregulated matters that require attention

#### Evaluate protection options presented by the Construction Firm to the Technical Inspection Team

#### Carry out on-site specialized inspections

#### Issue certificates of approval of the works

#### Definition of Consultancy Firms and Suppliers (See Chapter V)

#### The General Contractor’s main functions

#### Manage the administrative and legal aspects of the intended construction

#### Review upon receipt the architectural, structural, equipment, and detail plans

#### Review upon receipt all technical specifications

#### Ensure that the construction meets all the plan and specification requirements and permits set by law.

#### Ask suppliers to provide all safety certificates required

#### Supervise the pace at which the construction advances

#### Control all resources used in the construction

#### Carry out any tests needed to ensure the quality of the project

#### Produce reports on the progress of the construction

#### Establish program of payments to Suppliers and Subcontractors

#### Keep the Construction Log up to date

#### Carry out any other tasks stipulated in the contract

#### Definition of the Construction Firm’s responsibilities

#### Be fully aware of the details and objectives of the project

#### Acquire materials, hire labor, and arrange subcontracts of a quality befitting the requirements of the project

#### Assume responsibility for the actions of all subcontractors

#### Assume responsibility for the construction methods and sequences

#### Update the Construction Log in timely fashion

#### Respond in timely fashion to the requirements of the Institution and Coordination Team, Technical Inspection Team, Specialists, and External Inspectors

#### Provide access to external inspections, inspections by the Project Director, by the Technical Inspection Team and the other disciplines in charge of the design of the construction1

#### Report to the Technical Inspection Team any modification, voluntary or involuntary, to the original project

#### Report to the Technical Inspection and Coordination Teams in timely fashion the results of any tests

#### Assume responsibility for on-site safety during the construction process

#### Carry out any other tasks called for in the contract

#### Definition of the Technical inspection Team (See Chapter V)

#### Definition of the Technical Inspection Team’s Functions

#### Control the implementation of the construction program based on the performance objective assigned.

#### Review the construction procedures

#### Regularly engage in inspections regarding the quality of the construction materials used

#### Verify the quality of the labor employed

#### Assist the General Contractor in specific technical matters

#### Supervise the work of the external inspectors

#### Verify compliance with project specifications

#### Participate in the decision-making process in matters critical to the project or unregulated issues

#### Act as a permanent liaison between the Contractor and the Institution, the Project Director, and the Coordination Team

#### Continually check the construction log

#### Safeguard and control contractual documents

#### Verify the application of the correct safety measures during the construction process

#### Carry out any other contractual obligations

#### Definition of external bodies in charge of inspections and tests2

#### Produce an inspections and tests program3

#### Requirements affecting external inspection and test groups

#### Operate independently of the building firm

#### Be fully aware of the details and objectives of the project

#### Be fully aware of the plans and specifications of the project

#### Be fully aware of the stages of the construction process

#### Continuously and effectively inspect the materials, equipment and procedures used in the construction4

#### Extract representative samples based on the methods and materials employed on the construction

#### Report to the Construction Firm and the Technical Inspection in timely fashion (See Table 29)

#### Carry out any other tasks called for in the contract

#### Definition of channels and protocols of communication of results of trials and tests

#### From the body in charge of inspections to the Construction Firm

#### From the Construction Firm to the Technical Inspection Team

#### From the Technical Inspection Team to the Design Team and the Institution

#### As-Built Report on the facility5

#### Listing of professionals and specialists that participated in the project

#### Reports on regional and local risk (if applicable)

#### Definitive calculation logs

#### Construction Log and related documents

#### Inspection Reports

#### Test results

#### Safety certificates for the components, and certification of correct construction practices

#### Listing of codes and standards that were applied

#### As-built plans of architectural components and furniture

#### As-built plans of the structural system

#### As-built plans of the mechanical and electrical systems and equipment

#### As-built plans of basic facilities, clinical gases, ducts, A/C, fire extinguishing network, etc.

#### Other As-built information as defined by the Institution and the Coordination Team

#### Definition of criteria for acceptance of the works

#### Effective conclusion of the works stipulated in the contract

#### Compliance with the specifications of the project

#### Approval of As-built Report

#### Satisfactory implementation of tests on the operation of services, systems and equipment

#### Fines paid

#### Return of deposits

#### Reception of the construction by fiscal bodies

#### Delivery of the construction to the institution

#### Signed minutes of final reception of the works

#### Other criteria stipulated in the contract

| Notes: | 1 | The Client Institution or the specialists that participated in the design stage may demand that the Construction Firm stop the works if the safety requirements and quality standards stipulated in the project documents are not being met. |
| --- | --- | --- |
|  | 2 | All equipment and tools used in the inspections, trials or tests must have certificates of calibration issued by a recognized institution. |
|  | 3 | The body in charge of the trials and tests must have permanent access to the construction site. |
|  | 4 | The body in charge of the trials and tests may reject the use of particular materials and equipment. |
|  | 5 | The As-Built Report must be produced for any building with a functional or investment protection objective. For buildings with a life-safety performance objective, the As-Built Report must be produced if is expressly requested by the Institution, the Project Director or the Coordination Team. |

The following table lists the key contents of the construction inspection report.

Table 29 Characteristics of Inspection Reports

Inspection or Test Report

General Information (date, hour, etc.)

Staff in charge of the inspection or test

Procedures employed during inspection or test

List of equipment used during the inspection or test

Certificate from body in charge of calibrating the equipment and tools used in the inspection process

Results of the inspection or test

Characteristics of the materials inspected or tested

Characteristics of construction processes inspected

Results of the tests of materials or tests of operation

Inspected activities carried out or completed in compliance with project plans and specifications

Aspects in which there is no compliance with the project plans, specifications, standards and/or codes

Report of Non-compliance

Description of the non-compliant feature (including text and/or sketch specifying how aspect does not comply with the plans, etc.).

Location of the non-compliant feature

Qualitative description of the non-compliant feature

Other characteristics of the non-compliant feature

Actions needed to correct non-compliance

Processes that must be modified in order to prevent the recurrence of non-compliance

Deadlines for correcting the problem

- References

Applied Technology Council, ATC 51: U.S.-Italy Collaborative Recommendations for Improving the Seismic Safety of Hospitals in Italy, California, 2000.

Building Officials Code Administrators International, International Building Code 2000.

Building Seismic Safety Council (BSSC), FEMA 368: NEHRP Recommended Provisions for Seismic Regulations for New Buildings and Other Structures, Washington, D.C., 2001.

Building Seismic Safety Council (BSSC), FEMA 369: NEHRP Recommended Provisions for Seismic Regulations for New Buildings and Other Structures, Commentary, Washington, D.C., 2001.

Department of the Army, ER 5-1-11: U.S. Army Corps of Engineers Business Process, Management, Regulation, Washington, D.C., August 2001.

Departments of the Army, the Navy and the Air Force, NAVY NAVFAC P-355.1: Seismic Design Guidelines for Essential Buildings, Technical Manual, Washington, D.C., December 1986.

Departments of the Army, the Navy and the Air Force, NAVY NAVFAC P-355.2: Seismic Design Guidelines for Upgrading Existing Buildings, Technical Manual, Washington, D.C., September 1988.

European Committee for Standardization, Eurocode 8: Design of Structures for Earthquake Resistance. Part 1: General Rules, Seismic Actions and Rules for Buildings, Brussels, 1998.

Federal Emergency Management Agency, FEMA 310: Handbook for the Seismic Evaluation of Existing Buildings, Washington, D.C., 1998.

Federal Emergency Management Agency, FEMA 356: Prestandard and Commentary for the Seismic Rehabilitation of Buildings, Washington, D.C., November 2000.

Federal Emergency Management Agency, FEMA 74: Reducing the Risk of Nonstructural Earthquake Damage, A Practical Guide, Washington, D.C., September 1994.

International Standards Organization, ISO 12491:1997: Statistical Methods for Quality Control of Building Materials and Components.

International Standards Organization, ISO 13485:1996: Quality Systems, Medical Devices, Particular Requirements for the Application of ISO 9001.

International Standards Organization, ISO 13488:1996: Quality Systems, Medical Devices, Particular Requirements for the Application of ISO 9002.

International Standards Organization, ISO 9000:2000: Quality Management Systems, Fundamentals and Vocabulary.

International Standards Organization, ISO 9001:2000: Quality Management Systems, Requirements.

International Standards Organization, ISO 9002:1994: Quality Systems, Model for Quality Assurance in Production, Installation and Servicing.

International Standards Organization, ISO 9003:1994: Quality Systems, Model for Quality Assurance in Final Inspection and Test.

Office of Statewide Health Planning and Development (OSHPD), Building Standard Administrative Code, Part 1, Title 24, C.C.R, December 2001.

Patrucco, H., and G. McGavin, Survey of Non Structural Damage to Healthcare Facilities in the January 17, 1994 Northridge Earthquake.

Sistema Nacional de Protección Civil, Centro Nacional de Prevención de Desastres (CENAPRED), Calidad en Diseño, Construcción y Supervisión de Obras: Comparación de la Práctica en México, Japón y EUA, Memoria del Taller, 23 – 27 de Agosto, Mexico, 1993.

U.S. Army Corps of Engineers, Engineering Division, Directorate of Military Programs, TI 809-4: Seismic Design for Buildings, Technical Instructions, Washington, D.C., December 1998.

Cif. PAHO/WHO Collaborating Center on Disaster Mitigation in Health Facilities, Bases Metodológicas: Evaluación de Vulnerabilidad Sísmica de Edificaciones Estructuradas con Pórticos de Concreto Preformado, Evaluación de Elementos Arquitectónicos y Evaluación de Equipamiento, Universidad de Chile, 2000